Flood bund update Teams meeting 16/07/2026

Present, A. James, G. Chandler, T. Cox, M. Maginnis, N. Churchill, J. Beal, Lisa Stevens

Importing material: From today material is permitted to be imported from Upton Marina. Due to this much more local source, productivity on site will naturally improve. 650 tonnes of material have been brought in so far.
Timescales: Still on track to complete earth works in September
If weather holds and no interruptions at Upton, the going forward the work will continue at a fair rate
Drainage: Drainage works continue with 5 gangs on site, 1 gang has completed their section and has moved to assist the others.
Residents: no complaints or concerns have been received from residents since the last Teams call.

Next meeting in August will be cancelled due to holidays. Next scheduled Teams meeting is in September. Stop gap meetings will be arranged if the situation changes.
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